## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ameena Meethale Thayyil | 2025-02-25 | Error in setting up Python environment | 3 | Self | Logical | Updated Python version | 2025-02-26 | Closed | Conflicting Python versions in the system caused the error
2 | Ameena Meethale Thayyil | 2025-03-06 | Issue in integrating GUI | 7 | Self | User Interface | Simplified the chatbot interface and step by step debugging | 2025-03-07 | Closed | Worked with GUI step by step

## Sheet2
Logical
User Interface
Maintainability
Standards
Others